## Sheet1
Day | Time | Task
2022-09-23 | 5H | Meeting: Planning project structure and requirements
| 1H | Base frontend/backend projects structure and repos
2022-09-24 | 4H | Meeting: Creating class diagrams and review wireframs
| 2H | Continue with project structures
2022-09-25 | 5H | Integrating resource server with Keycloak
2022-09-26 | 5H | Implementing a few API endpoints
2022-09-27 | 5H | User sign in and redirecting to proper page based on user role
2022-09-30 | 5H | Enable user sign up, password reset flows
2022-10-01 | 2H | Dockerfile & Docker compose files for deploying keycloak & postgres
2022-10-02 | 1H | Demo video recording